## Cover
| PT. TEKNOLOGI REKAYASA KATUP |  |  |  |  | Document No.
| INSPECTION AND TEST PLAN |  |  |  |  | Revision:
| CUSTOMER |  |  | :
| CUSTOMER REFERENCE |  |  | :
| PROJECT |  |  | :
| REFERENCE |  |  | :
| LOCATION |  |  | :
| SALES ORDER NO. |  |  | :
| ITEMS |  |  | :
No. | Date | Prepared | Approved |  | Description

## Final
|  | PT. TEKNOLOGI REKAYASA KATUP | [6 empty] | Document No.
|  | INSPECTION AND TEST PLAN | [6 empty] | Revision:
| Customer | :
| End User | :
| SO NO. | :
| Product | :
| Size & Class | :
No. | ACTIVITY |  | PROCEDURE | ACCEPTANCE | APPLICABILITY | INSPECTION INVOLVEMENT |  |  | VERIFYING
[6 empty] | TRK | C | T | DOCUMENT
1 | PRE-MANUFACTURING ACTIVITIES
Legend :
M | : Monitoring
Q.C. surveillance activity including review of documentation
R | : Review
A check carried out on the certificates and / or report
W | : Witness
Witness (a request for inspection must be issued to the Customer/Third Party Inspection Agency.
H | : Hold Point
Hold (a request for inspection must be issued to the Customer/Third Party Inspection Agency as indicated in the 'Inspection Code' column;
work may not proceed without their attendance).
Abbrevation:
TRK |  | : PT. Teknologi Rekayasa Katup
T |  | : Third Party Inspection Agency
C |  | : Customer
Form No : TRK-PF-QA/QC-003-D Rev 02 Effective date: 13 Oct 2017

## BLV #600 A350 LF2 (B) (hidden)
|  | PT. TEKNOLOGI REKAYASA KATUP | [5 empty] | TRK-PF-QA/QC-003-D Revision: 0 Effective date: Feb, 01, 2016
INSPECTION AND TEST PLAN
| Customer | : | NA |  |  | Date | : | April 26, 2016
| End User | : | - |  |  | Document No. | : | 002/ITP/EG/TRK/IV/2016
| Tender No. | : | -
| P.O. No. | :
| Product | : | SOFT SEAT BALL VALVE, LTCS A350 Gr.LF2, SEAT SPE&DPE,
FULL BORE, BOLTED CLOSURE, BALL A350+ENP ,STEM AISI 4130+ENP, RF-FLANGED,
TRUNNION MOUNTED,
| Size & Class | : | 8" ANSI CLASS 600LB
No. | ACTIVITY |  |  | PROCEDURE | ACCEPTANCE | INSPECTION INVOLVEMENT |  | VERIFYING
[6 empty] | TRK | T | DOCUMENT
1 | REQUIREMENT REVIEW
| A) Drawing |  |  | TRK-P-EG-001 | API 6D , Edition 24th | R | - | Manufacture Drawing
Design and Development
| B) ITP Acceptance |  |  | TRK-P-QA/QC-003 |  | R | -
2 | MATERIAL
| A) Product Analysis |  |  | ASTM A751 | TRK-BV-R-001 | R | - | Materials Test Certificate
ASTM A350 LF2
| B) Mechanical Properties |  |  | ASTM A370 | TRK-BV-R-001 | R | - | Materials Test Certificate
ASTM A350 LF2
| C) Liquid Penetrant Examination |  |  | TRK-IF-QAQC-009-A | ASME V & VIII Div.1 Edition 2015 | H | - | MPE Report
| D) Marking |  |  | TRK-I-QA/QC-005 | API 6D , Edition 24th | H | - | Inspection Report
3 | MACHINING
| A) Visual Examination |  |  | TRK-I-QA/QC-002 | MSS-SP-55 Edition 2011 | H | - | Inspection Report
| B) Dimensional |  |  | TRK-PF-QAQC-013-A | TRK Drawings | H | - | Inspection Report
4 | ASSEMBLY |  |  | TRK-I-PO-014 Assembly Ball Valve
| A) Marking |  |  |  | API 6D , Edition 24th | H | - | Inspection Report
| B) Dimension Inspection |  |  |  |  | H | - | Inspection Report
| Flange Thickness |  |  |  | ASME B16.5 Edition 2013
| OD Flange |  |  |  | ASME B16.5 Edition 2013
| Face to Face |  |  |  | API 6D , Edition 24th
5 | PRESSURE TESTING |  |  | TRK-IF-QAQC-003-A | API 6D , Edition 24th | H | - | Pressure Test Report
| A) Shell Test |  |  |  | 2220 Psig
| B) Low- Pressure Closure |  |  |  | 80 Psig
| C) High - Pressure Closure |  |  |  | 1628 Psig
6 | FINAL INSPECTION
| A) Painting |  |  | TRK-QAQC--004-A | Manuf's Standard | H | - | Painting Report
Inspection Report
|  | PT. TEKNOLOGI REKAYASA KATUP | [5 empty] | TRK-PF-QA/QC-003-D Revision: 0 Effective date: Feb, 01, 2016
INSPECTION AND TEST PLAN
No. | ACTIVITY/ DESCRIPTION |  |  | APPLICABLE | ACCEPTANCE | INSPECTION INVOLVEMENT |  | VERIFYING
|  |  |  | STANDARD | CRITERIA | TRK | T | DOCUMENT
7 | PRESERVATION ,
PACKAGING DELIVERY
| A) Packaging |  |  | TRK-P-PO-004 | Manuf's Standard | H | - | Packaging List
| B) Issue For Final |  |  | TRK-P-QA/QC-004 |  | H | - | Final Check List
| Acceptance Notice | [6 empty] | Report
8 | DOCUMENTATION
| Manufacturer's Data Report |  |  | TRK MR |  | H | -
Legend :
R | : Record Review.
Client, or 3rd Party shall review inspection record.
SW | : Spot Witness.
TRK not required notifying client, or 3rd Party the timing of inspection test. Spot witness may be performed during witness inspection or when deemed necessary .
PMS | : Painting Manufacturer's Specification.
W | : Witness.
Client or 3rd Party witness inspection . However inspection and test is performed as scheduled, and even if the client, or 3rd party are not present. (requires notification).
A | : Approved.
NA | : Not Approved.
TRK | : PT. Teknologi Rekayasa Katup.
T | : Third Party Inspection Agency.
H | : Hold Point.
Client, or 3rd party requires notification of the inspection/test timing and inspection/test shall be carried out with client or 3rd party in attendance.
No Activity is permit without inspector attend.
NOTE | : " H " in TRK column is intended for TRK QC Department.