## RF
|  |  | PT. TEKNOLOGI REKAYASA KATUP | [16 empty] | Form No: TRK-PF-QA/QC-007-A Revision: 01 Effective date: March 01, 2017
TRACEABILITY REPORT
Report No. |  | : | 0001/TR/I/2018 | [9 empty] | PPO No. |  | : | 0002/PPO/2017
Customer |  | : | PT. Multi Superindo Manunggal | [9 empty] | Valve Type |  | : | Ball Valve
PO No. |  | : | POP.4479_Rev.0 | [9 empty] | Qty |  | : | 7 EA
SO No. |  | : | 0001/SO/2017 Rev. 0 | [9 empty] | Page |  | : | 1 |  | of | 2
SN | Part Name / No |  |  | Size In | Class | Material | Incoming |  |  | Machining Process & Inspection | [5 empty] | Assembling | Antistatic | Pressure Test | Cavity ReliefTesting | Blasting & Painting | Final Inspection | Status
[7 empty] | Hardness Testing | PMI | Dimensional Inspection | Machining | Dimensional Inspection | NDE
[12 empty] | PT | UT | MT
000117-1-1 | Body |  |  | 16 | 300 | ASTM A350 Gr. LF2 | 2017-12-04 |  | 2017-12-04 | 2017-12-16 | 2017-12-16 | 2017-12-17 |  |  |  | 2017-12-25 | 2017-12-26 | 2017-12-29 | - | 2018-01-08 | 2018-01-11 | ACC
| Closure |  |  |  |  | ASTM A350 Gr. LF2 | 2017-11-07 |  | 2017-11-07 | 2017-12-22 | 2017-12-22 | 2017-12-22 | 2017-12-08
| Ball |  |  |  |  | ASTM A350 Gr. LF2 + 0.08mm ENP | 2017-11-11 |  | 2017-11-11 | 2017-12-22 | 2017-12-27 | 2017-12-27
| Seat |  |  |  |  | ASTM A350 Gr. LF2 + 0.08mm ENP |  |  | 2017-12-15
| Stem |  |  |  |  | AISI 4140 + 0.08mm ENP | 2017-10-17 |  | 2017-10-17 | 2017-11-09 | 2017-11-09 | 2017-12-21
000117-1-2 | Body |  |  | 16 | 300 | ASTM A350 Gr. LF2 | 2017-12-12 |  | 2017-12-12 | 2017-12-18 | 2017-12-21 | 2017-12-23 |  |  |  | 2017-12-27 | 2017-12-27 | 2017-12-30 | - | 2018-01-08 | 2018-01-11 | ACC
| Closure |  |  |  |  | ASTM A350 Gr. LF2 | 2017-12-12 |  | 2017-12-12 | 2017-12-26 | 2017-12-26 | 2017-12-25 | 2017-12-24
| Ball |  |  |  |  | ASTM A350 Gr. LF2 + 0.08mm ENP | 2017-12-12 |  | 2017-12-12 | 2017-12-17 | 2017-12-19 | 2017-12-22
| Seat |  |  |  |  | ASTM A350 Gr. LF2 + 0.08mm ENP | 2017-12-12 |  | 2017-12-12
| Stem |  |  |  |  | AISI 4140 + 0.08mm ENP | 2017-10-17 |  | 2017-10-17 | 2017-11-09 | 2017-11-09 | 2017-12-21
000117-1-3 | Body |  |  | 16 | 300 | ASTM A350 Gr. LF2 | 2017-12-12 |  | 2017-12-12 | 2017-12-18 | 2017-12-21 | 2017-12-22 |  |  |  | 2017-12-29 | 2017-12-29 | 2018-01-02 | - | 2018-01-08 | 2018-01-11 | ACC
| Closure |  |  |  |  | ASTM A350 Gr. LF2 | 2017-12-12 |  | 2017-12-12 | 2017-12-27 | 2017-12-27 | 2017-12-25 | 2017-12-24
| Ball |  |  |  |  | ASTM A350 Gr. LF2 + 0.08mm ENP | 2017-12-12 |  | 2017-12-12 | 2017-12-17 | 2017-12-19 | 2017-12-19
| Seat |  |  |  |  | ASTM A350 Gr. LF2 + 0.08mm ENP | 2017-12-12 |  | 2017-12-12
| Stem |  |  |  |  | AISI 4140 + 0.08mm ENP | 2017-10-17 |  | 2017-10-17 | 2017-11-09 | 2017-12-09 | 2017-12-21
000117-1-4 | Body |  |  | 16 | 300 | ASTM A350 Gr. LF2 | 2017-12-12 |  | 2017-12-12 | 2017-12-18 | 2017-12-19 | 2017-12-22 |  |  |  | 2017-12-28 | 2017-12-30 | 2018-01-02 | - | 2018-01-08 | 2018-01-11 | ACC
| Closure |  |  |  |  | ASTM A350 Gr. LF2 | 2017-12-12 |  | 2017-12-12 | 2017-12-27 | 2017-12-27 | 2017-12-25 | 2017-12-24
| Ball |  |  |  |  | ASTM A350 Gr. LF2 + 0.08mm ENP | 2017-12-12 |  | 2017-12-12 | 2017-12-17 | 2017-12-22 | 2017-12-23
| Seat |  |  |  |  | ASTM A350 Gr. LF2 + 0.08mm ENP | 2017-12-12 |  | 2017-12-12
| Stem |  |  |  |  | AISI 4140 + 0.08mm ENP | 2017-10-17 |  | 2017-10-17 | 2017-11-09 | 2017-12-09 | 2017-12-19
| Prepared by, | [6 empty] | Reviewed by,

## WE
|  |  | PT. TEKNOLOGI REKAYASA KATUP | [16 empty] | Form No: TRK-PF-QA/QC-007-A Revision: 01 Effective date: March 01, 2017
TRACEABILITY REPORT
Report No. |  | : | 0001/TR/I/2018 | [9 empty] | PPO No. |  | : | 0002/PPO/2017
Customer |  | : | PT. Multi Superindo Manunggal | [9 empty] | Valve Type |  | : | Ball Valve
PO No. |  | : | POP.4479_Rev.0 | [9 empty] | Qty |  | : | 7 EA
SO No. |  | : | 0008/SO/2017 Rev. 1 | [9 empty] | Page |  | : | 2 |  | of | 2
SN | Part Name / No |  |  | Size In | Class | Material | Incoming |  |  | Machining Process & Inspection | [5 empty] | Assembling | Antistatic | Pressure Test | Cavity ReliefTesting | Blasting & Painting | Final Inspection | Status
[7 empty] | Hardness Testing | PMI | Dimensional Inspection | Machining | Dimensional Inspection | NDE
[12 empty] | PT | UT | MT
000117-2-1 | Body |  |  | 16 | 300 | ASTM A350 Gr. LF2 | 2017-12-12 |  | 2017-12-12 | 2017-12-20 | 2017-12-20 | 2017-12-22 |  |  |  | 2017-12-26 | 2017-12-26 | 2017-12-29 | - | 2018-01-08 | 2018-01-12 | ACC
| Closure |  |  |  |  | ASTM A350 Gr. LF2 | 2017-11-11 |  | 2017-11-11 | 2017-12-22 | 2017-12-22 | 2017-12-23 | 2017-12-06
| Closure |  |  |  |  | ASTM A350 Gr. LF2 | 2017-12-12 |  | 2017-12-12 | 2017-12-22 | 2017-12-22 | 2017-12-28 | 2017-12-26
| Ball |  |  |  |  | ASTM A350 Gr. LF2 + 0.08mm ENP | 2017-12-12 |  | 2017-12-12 | 2017-12-18 | 2017-12-22 | 2017-12-22
| Seat |  |  |  |  | ASTM A350 Gr. LF2 + 0.08mm ENP | 2017-12-12 |  | 2017-12-12
| Stem |  |  |  |  | AISI 4140 + 0.08mm ENP | 2017-10-17 |  | 2017-10-17 | 2017-11-09 | 2017-11-10 | 2017-12-21
000117-2-2 | Body |  |  | 16 | 300 | ASTM A350 Gr. LF2 | 2017-12-12 |  | 2017-12-12 | 2017-12-21 | 2017-12-21 | 2017-12-23 |  |  |  | 2017-12-28 | 2017-12-30 | 2017-12-29 | - | 2018-01-08 | 2018-01-12 | ACC
| Closure |  |  |  |  | ASTM A350 Gr. LF2 | 2017-12-12 |  | 2017-12-12 | 2017-12-26 | 2017-12-26 | 2017-12-25 | 2017-12-26
| Ball |  |  |  |  | ASTM A350 Gr. LF2 + 0.08mm ENP | 2017-12-12 |  | 2017-12-12 | 2017-12-17 | 2017-12-19 | 2017-12-19
| Seat |  |  |  |  | ASTM A350 Gr. LF2 + 0.08mm ENP | 2017-12-12 |  | 2017-12-12
| Stem |  |  |  |  | AISI 4140 + 0.08mm ENP | 2017-10-17 |  | 2017-10-17 | 2017-11-09 | 2017-11-10 | 2017-12-21
000117-2-3 | Body |  |  | 16 | 300 | ASTM A350 Gr. LF2 | 2017-12-12 |  | 2017-12-12 | 2017-12-21 | 2017-12-28 | 2017-12-23 |  |  |  | 2017-12-28 | 2017-12-31 | 2017-12-29 | - | 2018-01-08 | 2018-01-12 | ACC
| Closure |  |  |  |  | ASTM A350 Gr. LF2 | 2017-12-12 |  | 2017-12-12 | 2017-12-27 | 2017-12-28 | 2017-12-28 | 2017-12-26
| Ball |  |  |  |  | ASTM A350 Gr. LF2 + 0.08mm ENP | 2017-12-12 |  | 2017-12-12 | 2017-12-17 | 2017-12-28 | 2017-12-21
| Seat |  |  |  |  | ASTM A350 Gr. LF2 + 0.08mm ENP | 2017-12-12 |  | 2017-12-12
| Stem |  |  |  |  | AISI 4140 + 0.08mm ENP | 2017-10-17 |  | 2017-10-17 | 2017-11-09 | 2017-11-10 | 2017-12-21
| Prepared by, | [6 empty] | Reviewed by,

## 0008-S0
|  |  | PT. TEKNOLOGI REKAYASA KATUP | [18 empty] | Form No: TRK-PF-QA/QC-007-A Revision: 02 Effective date: January 25, 2018
TRACEABILITY REPORT
Report No. |  | : | [12 empty] | PPO No. |  | :
Customer |  | : | [12 empty] | Valve Type |  | :
PO No. |  | : | [12 empty] | Qty |  | :
SO No. |  | : | [12 empty] | Page |  | : |  |  | of
SN | Part Name / No |  |  | Size In | Class | Material | Incoming | [5 empty] | Machining Process & Inspection |  |  |  |  | Assembling | Antistatic | Pressure Test | Cavity ReliefTesting | Blasting & Painting | Final Inspection | Status
[7 empty] | Hardness Testing | PMI | Dimensional Inspection | NDE |  |  | Dimensional Inspection | NDE
[10 empty] | PT | UT | MT |  | PT | UT | MT
| Prepared by, | [6 empty] | Reviewed by,