## Analisis TRK
No | MODUL | MENU | TEST | PRGRESS | VIEW | NEW | UPDATE | DELETE | PRINT
1 | Purchasing | 7 | 1 | 16.67% | 16.67% | 16.67% | 16.67% | 16.67% | 16.67%
2 | Sales | 17 | 4 | 15.71% | 28.57% | 16.67% | 16.67% | 16.67% | 0%
3 | Finance | 42 | 0 | 0% | 0% | 0% | 0% | 0% | 0%
4 | Inventory | 11 | 0 | 0% | 0% | 0% | 0% | 0% | 0%
5 | Master | 57 | 31 | 41.32% | 52.63% | 47.37% | 49.12% | 48.21% | 9.259%
6 | Accounting | 9 | 0 | 0% | 0% | 0% | 0% | 0% | 0%
7 | E Faktur | 2 | 0 | 0% | 0% | 0% | 0% | 0% | 0%
8 | Report Finance | 2 | 0 | 0% | 0% | 0% | 0% | 0% | 0%

## PMT TRK
No | Module | Menu | Progress | View | New | Update | Delete | Print | Paper Size - Orientation | Document Number | Remark
1 | Purchasing | Purchase Request |  | 0% | 0% | 0% | 0% | 0% | 1/2 Letter - potrait | 1PRQ11/2001/0001
2 | Purchasing | Purchase Request Closing |  | 0% | 0% | 0% | 0% | 0%
3 | Purchasing | Purchase Order | 100% | 100% | 100% | 100% | 100% | 100% | 1/2 Letter - potrait | 1PUO11/2001/0001
4 | Purchasing | Purchase Order Approval |  | 0% | 0% | 0% | 0% | 0%
5 | Purchasing | Purchase Order Closing |  | 0% | 0% | 0% | 0% | 0%
6 | Purchasing | Purchase Return |  | 0% | 0% | 0% | 0% | 0% | 1/2 Letter - potrait | 1PRT19090001
7 | Purchasing | Purchase History
8 | Sales | Sales Order | 100% | 100% | 100% |  | 100% | 0% | 1/2 Letter - potrait | 1SAO11/2001/0001
9 | Sales | Sales Order Approval | 100% | 100% |  | 100% |  | 0%
10 | Sales | Sales Order Closing | 100% | 100% |  | 100%
11 | Sales | Picking List Sales Order | 100% | 100% | 100% |  | 100% | 0% | 1/2 Letter - potrait | 1PCL11/2001/0001
12 | Sales | Picking List Sales Order Confirmation |  | 0% | 0% | 0% | 0% | 0%
13 | Sales | Sales Contract |  | 0% | 0% | 0% | 0% | 0%
14 | Sales | Sales Contract Approval |  | 0% | 0% | 0% | 0% | 0%
15 | Sales | Sales Contract Closing |  | 0% | 0% | 0% | 0% | 0%
16 | Sales | Picking List Sales Contract
17 | Sales | Picking List Sales Contract Confirmation
18 | Sales | Delivery Note | [6 empty] | 1/2 Letter - potrait | 1SUJ11/2001/0001
19 | Sales | Return by Picking List |  | 0% | 0% | 0% | 0% | 0%
20 | Sales | Return by Delivery Note |  | 0% | 0% | 0% | 0% | 0%
21 | Sales | Return by Customer |  | 0% | 0% | 0% | 0% | 0%
22 | Sales | Return by Customer - Confirmation |  | 0% | 0% | 0% | 0% | 0%
23 | Finance | Customer Credit Note |  | 0% | 0% | 0% | 0% | 0%
24 | Finance | Customer Debit Note |  | 0% | 0% | 0% | 0% | 0%
25 | Finance | Vendor Credit Note |  | 0% | 0% | 0% | 0% | 0%
26 | Finance | Vendor Debit Note |  | 0% | 0% | 0% | 0% | 0%
27 | Finance | Payment Request |  | 0% | 0% | 0% | 0% | 0% | 1/2 Letter - potrait | 1PMR/2001/0001
28 | Finance | Payment Request Approval |  | 0% | 0% | 0% | 0% | 0%
29 | Finance | Cash Received |  | 0% | 0% | 0% | 0% | 0% | 1/2 Letter - potrait | 1CRV/2001/0001
30 | Finance | Bank Received |  | 0% | 0% | 0% | 0% | 0% | 1/2 Letter - potrait | 1BRV/2001/0001
31 | Finance | Cash Payment |  | 0% | 0% | 0% | 0% | 0% | 1/2 Letter - potrait | 1CAP/2001/0001
32 | Finance | Bank Payment |  | 0% | 0% | 0% | 0% | 0% | 1/2 Letter - potrait | 1BP-MDRT/2001/0001
33 | Finance | General Journal |  | 0% | 0% | 0% | 0% | 0% | 1/2 Letter - potrait | 1GJU/2001/0001
34 | Finance | Giro Received |  | 0% | 0% | 0% | 0% | 0% | 1/2 Letter - potrait | 1GRV2001/0001
35 | Finance | Giro Payment |  | 0% | 0% | 0% | 0% | 0% | 1/2 Letter - potrait | 1GP-MDRG/2001/0001
36 | Finance | Payment History |  | 0% | 0% | 0% | 0% | 0%
37 | Finance | Finance Recalculating |  | 0% | 0% | 0% | 0% | 0%
38 | Finance | Customer Deposit Assignment |  | 0% | 0% | 0% | 0% | 0%
39 | Finance | Vendor Deposit Assignment |  | 0% | 0% | 0% | 0% | 0%
40 | Finance | Vendor Invoice |  | 0% | 0% | 0% | 0% | 0% | 1/2 Letter - potrait | 1VIN11/2001/0001
41 | Finance | Customer Invoice |  | 0% | 0% | 0% | 0% | 0% | 1/2 Letter - potrait | 1INV11/2003/0001
42 | Finance | Update Customer Invoice Information |  | 0% | 0% | 0% | 0% | 0%
43 | Finance | Customer Invoice Confirmation |  | 0% | 0% | 0% | 0% | 0%
44 | Finance | Vendor Down Payment |  | 0% | 0% | 0% | 0% | 0% | 1/2 Letter - potrait | 1VDP11/2001/0001
45 | Sales | Tax Invoice Registration |  | 0% | 0% | 0% | 0% | 0%
46 | Sales | Tax Invoice Assignment |  | 0% | 0% | 0% | 0% | 0%
47 | Finance | Giro Received Reject |  | 0% | 0% | 0% | 0% | 0%
48 | Finance | Giro Payment Reject |  | 0% | 0% | 0% | 0% | 0%
49 | Finance | Giro Received Inquiry |  | 0% | 0% | 0% | 0% | 0%
50 | Finance | Giro Payment Inquiry |  | 0% | 0% | 0% | 0% | 0%
51 | Finance | Customer Credit Note Acc Supervisor |  | 0% | 0% | 0% | 0% | 0%
52 | Finance | Customer Debit Note Acc Supervisor |  | 0% | 0% | 0% | 0% | 0%
53 | Finance | Vendor Credit Note Acc Supervisor |  | 0% | 0% | 0% | 0% | 0%
54 | Finance | Vendor Debit Note Acc Supervisor |  | 0% | 0% | 0% | 0% | 0%
55 | Finance | Cash Received Acc Supervisor |  | 0% | 0% | 0% | 0% | 0%
56 | Finance | Bank Received Acc Supervisor |  | 0% | 0% | 0% | 0% | 0%
57 | Finance | Cash Payment Acc Supervisor |  | 0% | 0% | 0% | 0% | 0%
58 | Finance | Bank Payment Acc Supervisor |  | 0% | 0% | 0% | 0% | 0%
59 | Finance | Customer Down Payment |  | 0% | 0% | 0% | 0% | 0% | 1/2 Letter - potrait | 1CDP11/2001/0001
60 | Finance | Goods Received Note Posting |  | 0% | 0% | 0% | 0% | 0%
61 | Finance | Goods Received Note Posting Recalculating |  | 0% | 0% | 0% | 0% | 0%
62 | Finance | Goods Received Note Posting Closing |  | 0% | 0% | 0% | 0% | 0%
63 | Finance | VAT In |  | 0% | 0% | 0% | 0% | 0%
64 | Finance | VAT Out |  | 0% | 0% | 0% | 0% | 0%
65 | Finance | Invoice Delivery Note Check List |  | 0% | 0% | 0% | 0% | 0%
66 | Finance | Kwitansi |  | 0% | 0% | 0% | 0% | 0%
67 | Inventory | Goods Received Note by Purchase Order |  | 0% | 0% | 0% | 0% | 0% | 1/2 Letter - potrait | 1GRN11/2001/0001
68 | Inventory | Assembly Job Order |  | 0% | 0% | 0% | 0% | 0% | 1/2 Letter - potrait | 1AJO11/2001/0001
69 | Inventory | Assembly Realization |  | 0% | 0% | 0% | 0% | 0% | 1/2 Letter - potrait | 1AJR11/2001/0001
70 | Inventory | Adjustment In |  | 0% | 0% | 0% | 0% | 0% | 1/2 Letter - potrait | 1AI11/2001/0001
71 | Inventory | Adjustment In Approval |  | 0% | 0% | 0% | 0% | 0%
72 | Inventory | Adjustment Out |  | 0% | 0% | 0% | 0% | 0% | 1/2 Letter - potrait | 1ADJOUT11/2001/0001
73 | Inventory | Adjustment Out Approval |  | 0% | 0% | 0% | 0% | 0%
74 | Inventory | Warehouse Transfer Out |  | 0% | 0% | 0% | 0% | 0% | 1/2 Letter - potrait | 1WHTO11/2001/0001
75 | Inventory | Warehouse Transfer In |  | 0% | 0% | 0% | 0% | 0% | 1/2 Letter - potrait | 1WHTI11/2001/0001
76 | Inventory | Rack Mutation |  | 0% | 0% | 0% | 0% | 0%
77 | Inventory | Dock Stock |  | 0% | 0% | 0% | 0% | 0%
78 | Accounting | Unbalance Journal |  | 0% | 0% | 0% | 0% | 0%
79 | Accounting | Undetail Journal |  | 0% | 0% | 0% | 0% | 0%
80 | Accounting | Unheader Journal |  | 0% | 0% | 0% | 0% | 0%
81 | Accounting | Journal Posting |  | 0% | 0% | 0% | 0% | 0%
82 | Accounting | Accounting Closing |  | 0% | 0% | 0% | 0% | 0%
83 | Accounting | Journal Query |  | 0% | 0% | 0% | 0% | 0%
84 | Accounting | VAT In |  | 0% | 0% | 0% | 0% | 0%
85 | Accounting | VAT Out |  | 0% | 0% | 0% | 0% | 0%
86 | Accounting | Void tax Invoice |  | 0% | 0% | 0% | 0% | 0%
87 | Master | Asset Category | 100% | 100% | 100% | 100% | 100% | 100% | A4 - potrait | MANUAL
88 | Master | Asset Registration | 100% | 100% | 100% | 100% | 100% | 0% | A4 - potrait | MANUAL
89 | Master | Bank | 100% | 100% | 100% | 100% | 100% | 100% | A4 - potrait | MANUAL
90 | Master | Bank Account | 100% | 0% | 100% | 100% | 100% | 0% | A4 - potrait | MANUAL
91 | Master | Bill of Material | 100% | 100% | 100% | 100% | 100% | 0% | A4 - potrait | MANUAL
92 | Master | Branch | 100% | 100% | 100% | 100% | 100% | 0% | A4 - potrait | MANUAL
93 | Master | Cash Account | 100% | 100% | 100% | 100% | 100% | 0% | A4 - potrait | MANUAL
94 | Master | Chart of Account | 100% | 100% | 100% | 100% | 100% | 0% | A4 - potrait | MANUAL
95 | Master | City | 100% | 100% | 100% | 100% | 100% | 100% | A4 - potrait | MANUAL
96 | Master | Co - Driver | 100% | 100% | 100% | 100% | 100% | 0% | A4 - potrait | MANUAL
97 | Master | Country | 100% | 100% | 100% | 100% | 100% | 0% | A4 - potrait | MANUAL
98 | Master | Currency | 100% | 100% | 100% | 100% | 100% | 0% | A4 - potrait | MANUAL
99 | Master | Current Stock COGSIDR | 100% | 100% | 0% | 0% | 0% | 100%
100 | Master | Current Stock Quantiy | 100% | 100% | 0% | 0% | 0% | 100%
101 | Master | Customer | 100% | 100% | 100% | 100% | 100% | 0% | A4 - potrait | MANUAL
102 | Master | Customer Address | 100% | 100% | 100% | 100% | 100% | 0% | A4 - potrait | MANUAL
103 | Master | Customer Category | 100% | 100% | 100% | 100% | 100% | 0% | A4 - potrait | MANUAL
104 | Master | Customer Contact | 100% | 100% | 100% | 100% | 100% |  | A4 - potrait | MANUAL
105 | Master | Distribution Channel | 100% | 100% | 100% | 100% | 100% | 0% | A4 - potrait | MANUAL
106 | Master | Driver | 100% | 100% | 100% | 100% | 100% | 0% | A4 - potrait | MANUAL
107 | Master | Education | 100% | 100% | 100% | 100% | 100% | 0% | A4 - potrait | MANUAL
108 | Master | Employee | 100% | 100% | 100% | 100% | 100% | 0% | A4 - potrait | MANUAL
109 | Master | Exchange Rate |  | 0% | 0% | 0% | 0% |  |  | MANUAL
110 | Master | Expedition | 100% | 100% | 100% | 100% | 100% | 0% | A4 - potrait | MANUAL
111 | Master | Island | 100% | 100% | 100% | 100% | 100% | 0% | A4 - potrait | MANUAL
112 | Master | Item | 100% | 100% | 100% | 100% | 100% | 0% | A4 - potrait | auto
113 | Master | Item Brand | 100% | 100% | 100% | 100% | 100% | 0% | A4 - potrait | MANUAL
114 | Master | Item Commission Range | 100% | 100% | 0% | 0% | 0% | 0%
115 | Master | Item Product Category | 100% | 100% | 100% | 100% | 100% | 0% | A4 - potrait | MANUAL
116 | Master | Item Product Head | 100% | 100% | 100% | 100% | 100% | 0% | A4 - potrait | MANUAL
117 | Master | Item Division | 100% | 100% | 100% | 100% | 100% | 0% | A4 - potrait | MANUAL
118 | Master | Journal | 100% | 100% | 0% | 100%
119 | Master | Payment Term |  | 0% | 0% | 0% | 0% | 0% | A4 - potrait | MANUAL
120 | Master | PPh Type |  | 0% | 0% | 0% | 0% | 0% | A4 - potrait | MANUAL
121 | Master | Price List |  | 0% | 0% | 0% | 0% | 0% | A4 - potrait | PRC_LST30032020090125END
122 | Master | Price List Approval |  | 0% | 0% | 0% | 0% | 0%
123 | Master | Price Type |  | 0% | 0% | 0% | 0% | 0% | A4 - potrait | MANUAL
124 | Master | Project |  | 0% | 0% | 0% | 0% | 0% | A4 - potrait | MANUAL
125 | Master | Promo Category ( Customer ) |  | 0% | 0% | 0% | 0% | 0% |  |  | SKIP
126 | Master | Promo ( Customer ) |  | 0% | 0% | 0% | 0% | 0% |  |  | SKIP
127 | Master | Promo Category ( Vendor ) |  | 0% | 0% | 0% | 0% | 0% |  |  | SKIP
128 | Master | Promo ( Vendor ) |  | 0% | 0% | 0% | 0% | 0% |  |  | SKIP
129 | Master | Province |  | 0% | 0% | 0% | 0% | 0% | A4 - potrait | MANUAL
130 | Master | Purchase Destination |  | 0% | 0% | 0% | 0% | 0% | A4 - potrait | MANUAL
131 | Master | Rack |  | 0% | 0% | 0% | 0% | 0% | A4 - potrait | MANUAL
132 | Master | Rack - Item |  | 0% | 0% | 0% | 0% | 0% | A4 - potrait | AUTO dari MST RACK
133 | Master | Rack Type |  | 0% | 0% | 0% | 0% | 0% | A4 - potrait | MANUAL
134 | Master | Reason |  | 0% | 0% | 0% | 0% | 0% | A4 - potrait | MANUAL
135 | Master | Religion |  | 0% | 0% | 0% | 0% | 0% | A4 - potrait | MANUAL
136 | Master | Sales Person |  | 0% | 0% | 0% | 0% | 0% | A4 - potrait | MANUAL
137 | Master | Target Head Product |  | 0% | 0% | 0% | 0% | 0% | A4 - potrait | MANUAL
138 | Master | Target Head Product Posting |  | 0% | 0% | 0% | 0% | 0% |  | AUTO dari MST Target Head Product
139 | Master | Unit Of Measure |  | 0% | 0% | 0% | 0% | 0% | A4 - potrait | MANUAL
140 | Master | Vendor |  | 0% | 0% | 0% | 0% | 0% | A4 - potrait | MANUAL
141 | Master | Vendor Category |  | 0% | 0% | 0% | 0% | 0% | A4 - potrait | MANUAL
142 | Master | Vendor Contact |  | 0% | 0% | 0% | 0% | 0% |  | VD_02003_00001
143 | Master | Warehouse |  | 0% | 0% | 0% | 0% | 0% | A4 - potrait | MANUAL
144 | System | Transaction Log |  | 0% | 0% | 0% | 0% | 0%
145 | Security | Change Password |  | 0% | 0% | 0% | 0% | 0%
146 | Security | Data Protection |  | 0% | 0% | 0% | 0% | 0%
147 | Security | Role |  | 0% | 0% | 0% | 0% | 0%
148 | Security | Role Authorization |  | 0% | 0% | 0% | 0% | 0%
149 | Security | User |  | 0% | 0% | 0% | 0% | 0%
150 | E Faktur | Masukan |  | 0% | 0% | 0% | 0% | 0%
151 | E Faktur | Keluaran |  | 0% | 0% | 0% | 0% | 0%
152 | Report Finance | AP Aging |  | 0% | 0% | 0% | 0% | 0%
153 | Report Finance | AR Aging |  | 0% | 0% | 0% | 0% | 0%

## Bug List TRK
No | Modul | Menu | Action | Status | Assign | Bug
1 | Accounting | Accounting Closing | VIEW | Pending
2 | Accounting | Accounting Closing | NEW | Pending
3 | Accounting | Accounting Closing | UPDATE | Pending
4 | Accounting | Accounting Closing | DELETE | Pending
5 | Accounting | Accounting Closing | PRINT | Pending
6 | Accounting | Journal Posting | VIEW | Pending
7 | Accounting | Journal Posting | NEW | Pending
8 | Accounting | Journal Posting | UPDATE | Pending
9 | Accounting | Journal Posting | DELETE | Pending
10 | Accounting | Journal Posting | PRINT | Pending
11 | Accounting | Journal Query | VIEW | Pending
12 | Accounting | Journal Query | NEW | Pending
13 | Accounting | Journal Query | UPDATE | Pending
14 | Accounting | Journal Query | DELETE | Pending
15 | Accounting | Journal Query | PRINT | Pending
16 | Accounting | Unbalance Journal | VIEW | Pending
17 | Accounting | Unbalance Journal | NEW | Pending
18 | Accounting | Unbalance Journal | UPDATE | Pending
19 | Accounting | Unbalance Journal | DELETE | Pending
20 | Accounting | Unbalance Journal | PRINT | Pending
21 | Accounting | Undetail Journal | VIEW | Pending
22 | Accounting | Undetail Journal | NEW | Pending
23 | Accounting | Undetail Journal | UPDATE | Pending
24 | Accounting | Undetail Journal | DELETE | Pending
25 | Accounting | Undetail Journal | PRINT | Pending
26 | Accounting | Unheader Journal | VIEW | Pending
27 | Accounting | Unheader Journal | NEW | Pending
28 | Accounting | Unheader Journal | UPDATE | Pending
29 | Accounting | Unheader Journal | DELETE | Pending
30 | Accounting | Unheader Journal | PRINT | Pending
31 | Accounting | VAT In | VIEW | Pending
32 | Accounting | VAT In | NEW | Pending
33 | Accounting | VAT In | UPDATE | Pending
34 | Accounting | VAT In | DELETE | Pending
35 | Accounting | VAT In | PRINT | Pending
36 | Accounting | VAT Out | VIEW | Pending
37 | Accounting | VAT Out | NEW | Pending
38 | Accounting | VAT Out | UPDATE | Pending
39 | Accounting | VAT Out | DELETE | Pending
40 | Accounting | VAT Out | PRINT | Pending
41 | Accounting | Void tax Invoice | VIEW | Pending
42 | Accounting | Void tax Invoice | NEW | Pending
43 | Accounting | Void tax Invoice | UPDATE | Pending
44 | Accounting | Void tax Invoice | DELETE | Pending
45 | Accounting | Void tax Invoice | PRINT | Pending
46 | E Faktur | Keluaran | VIEW | Pending
47 | E Faktur | Keluaran | NEW | Pending
48 | E Faktur | Keluaran | UPDATE | Pending
49 | E Faktur | Keluaran | DELETE | Pending
50 | E Faktur | Keluaran | PRINT | Pending
51 | E Faktur | Masukan | VIEW | Pending
52 | E Faktur | Masukan | NEW | Pending
53 | E Faktur | Masukan | UPDATE | Pending
54 | E Faktur | Masukan | DELETE | Pending
55 | E Faktur | Masukan | PRINT | Pending
56 | Finance | Bank Payment | VIEW | Pending
57 | Finance | Bank Payment | NEW | Pending
58 | Finance | Bank Payment | UPDATE | Pending
59 | Finance | Bank Payment | DELETE | Pending
60 | Finance | Bank Payment | PRINT | Pending
61 | Finance | Bank Payment Acc Supervisor | VIEW | Pending
62 | Finance | Bank Payment Acc Supervisor | NEW | Pending
63 | Finance | Bank Payment Acc Supervisor | UPDATE | Pending
64 | Finance | Bank Payment Acc Supervisor | DELETE | Pending
65 | Finance | Bank Payment Acc Supervisor | PRINT | Pending
66 | Finance | Bank Received | VIEW | Pending
67 | Finance | Bank Received | NEW | Pending
68 | Finance | Bank Received | UPDATE | Pending
69 | Finance | Bank Received | DELETE | Pending
70 | Finance | Bank Received | PRINT | Pending
71 | Finance | Bank Received Acc Supervisor | VIEW | Pending
72 | Finance | Bank Received Acc Supervisor | NEW | Pending
73 | Finance | Bank Received Acc Supervisor | UPDATE | Pending
74 | Finance | Bank Received Acc Supervisor | DELETE | Pending
75 | Finance | Bank Received Acc Supervisor | PRINT | Pending
76 | Finance | Cash Payment | VIEW | Pending
77 | Finance | Cash Payment | NEW | Pending
78 | Finance | Cash Payment | UPDATE | Pending
79 | Finance | Cash Payment | DELETE | Pending
80 | Finance | Cash Payment | PRINT | Pending
81 | Finance | Cash Payment Acc Supervisor | VIEW | Pending
82 | Finance | Cash Payment Acc Supervisor | NEW | Pending
83 | Finance | Cash Payment Acc Supervisor | UPDATE | Pending
84 | Finance | Cash Payment Acc Supervisor | DELETE | Pending
85 | Finance | Cash Payment Acc Supervisor | PRINT | Pending
86 | Finance | Cash Received | VIEW | Pending
87 | Finance | Cash Received | NEW | Pending
88 | Finance | Cash Received | UPDATE | Pending
89 | Finance | Cash Received | DELETE | Pending
90 | Finance | Cash Received | PRINT | Pending
91 | Finance | Cash Received Acc Supervisor | VIEW | Pending
92 | Finance | Cash Received Acc Supervisor | NEW | Pending
93 | Finance | Cash Received Acc Supervisor | UPDATE | Pending
94 | Finance | Cash Received Acc Supervisor | DELETE | Pending
95 | Finance | Cash Received Acc Supervisor | PRINT | Pending
96 | Finance | Customer Credit Note | VIEW | Pending
97 | Finance | Customer Credit Note | NEW | Pending
98 | Finance | Customer Credit Note | UPDATE | Pending
99 | Finance | Customer Credit Note | DELETE | Pending
100 | Finance | Customer Credit Note | PRINT | Pending
101 | Finance | Customer Credit Note Acc Supervisor | VIEW | Pending
102 | Finance | Customer Credit Note Acc Supervisor | NEW | Pending
103 | Finance | Customer Credit Note Acc Supervisor | UPDATE | Pending
104 | Finance | Customer Credit Note Acc Supervisor | DELETE | Pending
105 | Finance | Customer Credit Note Acc Supervisor | PRINT | Pending
106 | Finance | Customer Debit Note | VIEW | Pending
107 | Finance | Customer Debit Note | NEW | Pending
108 | Finance | Customer Debit Note | UPDATE | Pending
109 | Finance | Customer Debit Note | DELETE | Pending
110 | Finance | Customer Debit Note | PRINT | Pending
111 | Finance | Customer Debit Note Acc Supervisor | VIEW | Pending
112 | Finance | Customer Debit Note Acc Supervisor | NEW | Pending
113 | Finance | Customer Debit Note Acc Supervisor | UPDATE | Pending
114 | Finance | Customer Debit Note Acc Supervisor | DELETE | Pending
115 | Finance | Customer Debit Note Acc Supervisor | PRINT | Pending
116 | Finance | Customer Deposit Assignment | VIEW | Pending
117 | Finance | Customer Deposit Assignment | NEW | Pending
118 | Finance | Customer Deposit Assignment | UPDATE | Pending
119 | Finance | Customer Deposit Assignment | DELETE | Pending
120 | Finance | Customer Deposit Assignment | PRINT | Pending
121 | Finance | Customer Down Payment | VIEW | Pending
122 | Finance | Customer Down Payment | NEW | Pending
123 | Finance | Customer Down Payment | UPDATE | Pending
124 | Finance | Customer Down Payment | DELETE | Pending
125 | Finance | Customer Down Payment | PRINT | Pending
126 | Finance | Customer Invoice | VIEW | Pending
127 | Finance | Customer Invoice | NEW | Pending
128 | Finance | Customer Invoice | UPDATE | Pending
129 | Finance | Customer Invoice | DELETE | Pending
130 | Finance | Customer Invoice | PRINT | Pending
131 | Finance | Customer Invoice Confirmation | VIEW | Pending
132 | Finance | Customer Invoice Confirmation | NEW | Pending
133 | Finance | Customer Invoice Confirmation | UPDATE | Pending
134 | Finance | Customer Invoice Confirmation | DELETE | Pending
135 | Finance | Customer Invoice Confirmation | PRINT | Pending
136 | Finance | Finance Recalculating | VIEW | Pending
137 | Finance | Finance Recalculating | NEW | Pending
138 | Finance | Finance Recalculating | UPDATE | Pending
139 | Finance | Finance Recalculating | DELETE | Pending
140 | Finance | Finance Recalculating | PRINT | Pending
141 | Finance | General Journal | VIEW | Pending
142 | Finance | General Journal | NEW | Pending
143 | Finance | General Journal | UPDATE | Pending
144 | Finance | General Journal | DELETE | Pending
145 | Finance | General Journal | PRINT | Pending
146 | Finance | Giro Payment | VIEW | Pending
147 | Finance | Giro Payment | NEW | Pending
148 | Finance | Giro Payment | UPDATE | Pending
149 | Finance | Giro Payment | DELETE | Pending
150 | Finance | Giro Payment | PRINT | Pending
151 | Finance | Giro Payment Inquiry | VIEW | Pending
152 | Finance | Giro Payment Inquiry | NEW | Pending
153 | Finance | Giro Payment Inquiry | UPDATE | Pending
154 | Finance | Giro Payment Inquiry | DELETE | Pending
155 | Finance | Giro Payment Inquiry | PRINT | Pending
156 | Finance | Giro Payment Reject | VIEW | Pending
157 | Finance | Giro Payment Reject | NEW | Pending
158 | Finance | Giro Payment Reject | UPDATE | Pending
159 | Finance | Giro Payment Reject | DELETE | Pending
160 | Finance | Giro Payment Reject | PRINT | Pending
161 | Finance | Giro Received | VIEW | Pending
162 | Finance | Giro Received | NEW | Pending
163 | Finance | Giro Received | UPDATE | Pending
164 | Finance | Giro Received | DELETE | Pending
165 | Finance | Giro Received | PRINT | Pending
166 | Finance | Giro Received Inquiry | VIEW | Pending
167 | Finance | Giro Received Inquiry | NEW | Pending
168 | Finance | Giro Received Inquiry | UPDATE | Pending
169 | Finance | Giro Received Inquiry | DELETE | Pending
170 | Finance | Giro Received Inquiry | PRINT | Pending
171 | Finance | Giro Received Reject | VIEW | Pending
172 | Finance | Giro Received Reject | NEW | Pending
173 | Finance | Giro Received Reject | UPDATE | Pending
174 | Finance | Giro Received Reject | DELETE | Pending
175 | Finance | Giro Received Reject | PRINT | Pending
176 | Finance | Goods Received Note Posting | VIEW | Pending
177 | Finance | Goods Received Note Posting | NEW | Pending
178 | Finance | Goods Received Note Posting | UPDATE | Pending
179 | Finance | Goods Received Note Posting | DELETE | Pending
180 | Finance | Goods Received Note Posting | PRINT | Pending
181 | Finance | Goods Received Note Posting Closing | VIEW | Pending
182 | Finance | Goods Received Note Posting Closing | NEW | Pending
183 | Finance | Goods Received Note Posting Closing | UPDATE | Pending
184 | Finance | Goods Received Note Posting Closing | DELETE | Pending
185 | Finance | Goods Received Note Posting Closing | PRINT | Pending
186 | Finance | Goods Received Note Posting Recalculating | VIEW | Pending
187 | Finance | Goods Received Note Posting Recalculating | NEW | Pending
188 | Finance | Goods Received Note Posting Recalculating | UPDATE | Pending
189 | Finance | Goods Received Note Posting Recalculating | DELETE | Pending
190 | Finance | Goods Received Note Posting Recalculating | PRINT | Pending
191 | Finance | Invoice Delivery Note Check List | VIEW | Pending
192 | Finance | Invoice Delivery Note Check List | NEW | Pending
193 | Finance | Invoice Delivery Note Check List | UPDATE | Pending
194 | Finance | Invoice Delivery Note Check List | DELETE | Pending
195 | Finance | Invoice Delivery Note Check List | PRINT | Pending
196 | Finance | Kwitansi | VIEW | Pending
197 | Finance | Kwitansi | NEW | Pending
198 | Finance | Kwitansi | UPDATE | Pending
199 | Finance | Kwitansi | DELETE | Pending
200 | Finance | Kwitansi | PRINT | Pending
201 | Finance | Payment History | VIEW | Pending
202 | Finance | Payment History | NEW | Pending
203 | Finance | Payment History | UPDATE | Pending
204 | Finance | Payment History | DELETE | Pending
205 | Finance | Payment History | PRINT | Pending
206 | Finance | Payment Request | VIEW | Pending
207 | Finance | Payment Request | NEW | Pending
208 | Finance | Payment Request | UPDATE | Pending
209 | Finance | Payment Request | DELETE | Pending
210 | Finance | Payment Request | PRINT | Pending
211 | Finance | Payment Request Approval | VIEW | Pending
212 | Finance | Payment Request Approval | NEW | Pending
213 | Finance | Payment Request Approval | UPDATE | Pending
214 | Finance | Payment Request Approval | DELETE | Pending
215 | Finance | Payment Request Approval | PRINT | Pending
216 | Finance | Update Customer Invoice Information | VIEW | Pending
217 | Finance | Update Customer Invoice Information | NEW | Pending
218 | Finance | Update Customer Invoice Information | UPDATE | Pending
219 | Finance | Update Customer Invoice Information | DELETE | Pending
220 | Finance | Update Customer Invoice Information | PRINT | Pending
221 | Finance | VAT In | VIEW | Pending
222 | Finance | VAT In | NEW | Pending
223 | Finance | VAT In | UPDATE | Pending
224 | Finance | VAT In | DELETE | Pending
225 | Finance | VAT In | PRINT | Pending
226 | Finance | VAT Out | VIEW | Pending
227 | Finance | VAT Out | NEW | Pending
228 | Finance | VAT Out | UPDATE | Pending
229 | Finance | VAT Out | DELETE | Pending
230 | Finance | VAT Out | PRINT | Pending
231 | Finance | Vendor Credit Note | VIEW | Pending
232 | Finance | Vendor Credit Note | NEW | Pending
233 | Finance | Vendor Credit Note | UPDATE | Pending
234 | Finance | Vendor Credit Note | DELETE | Pending
235 | Finance | Vendor Credit Note | PRINT | Pending
236 | Finance | Vendor Credit Note Acc Supervisor | VIEW | Pending
237 | Finance | Vendor Credit Note Acc Supervisor | NEW | Pending
238 | Finance | Vendor Credit Note Acc Supervisor | UPDATE | Pending
239 | Finance | Vendor Credit Note Acc Supervisor | DELETE | Pending
240 | Finance | Vendor Credit Note Acc Supervisor | PRINT | Pending
241 | Finance | Vendor Debit Note | VIEW | Pending
242 | Finance | Vendor Debit Note | NEW | Pending
243 | Finance | Vendor Debit Note | UPDATE | Pending
244 | Finance | Vendor Debit Note | DELETE | Pending
245 | Finance | Vendor Debit Note | PRINT | Pending
246 | Finance | Vendor Debit Note Acc Supervisor | VIEW | Pending
247 | Finance | Vendor Debit Note Acc Supervisor | NEW | Pending
248 | Finance | Vendor Debit Note Acc Supervisor | UPDATE | Pending
249 | Finance | Vendor Debit Note Acc Supervisor | DELETE | Pending
250 | Finance | Vendor Debit Note Acc Supervisor | PRINT | Pending
251 | Finance | Vendor Deposit Assignment | VIEW | Pending
252 | Finance | Vendor Deposit Assignment | NEW | Pending
253 | Finance | Vendor Deposit Assignment | UPDATE | Pending
254 | Finance | Vendor Deposit Assignment | DELETE | Pending
255 | Finance | Vendor Deposit Assignment | PRINT | Pending
256 | Finance | Vendor Down Payment | VIEW | Pending
257 | Finance | Vendor Down Payment | NEW | Pending
258 | Finance | Vendor Down Payment | UPDATE | Pending
259 | Finance | Vendor Down Payment | DELETE | Pending
260 | Finance | Vendor Down Payment | PRINT | Pending
261 | Finance | Vendor Invoice | VIEW | Pending
262 | Finance | Vendor Invoice | NEW | Pending
263 | Finance | Vendor Invoice | UPDATE | Pending
264 | Finance | Vendor Invoice | DELETE | Pending
265 | Finance | Vendor Invoice | PRINT | Pending
266 | Inventory | Adjustment In | VIEW | Pending
267 | Inventory | Adjustment In | NEW | Pending
268 | Inventory | Adjustment In | UPDATE | Pending
269 | Inventory | Adjustment In | DELETE | Pending
270 | Inventory | Adjustment In | PRINT | Pending
271 | Inventory | Adjustment In Approval | VIEW | Pending
272 | Inventory | Adjustment In Approval | NEW | Pending
273 | Inventory | Adjustment In Approval | UPDATE | Pending
274 | Inventory | Adjustment In Approval | DELETE | Pending
275 | Inventory | Adjustment In Approval | PRINT | Pending
276 | Inventory | Adjustment Out | VIEW | Pending
277 | Inventory | Adjustment Out | NEW | Pending
278 | Inventory | Adjustment Out | UPDATE | Pending
279 | Inventory | Adjustment Out | DELETE | Pending
280 | Inventory | Adjustment Out | PRINT | Pending
281 | Inventory | Adjustment Out Approval | VIEW | Pending
282 | Inventory | Adjustment Out Approval | NEW | Pending
283 | Inventory | Adjustment Out Approval | UPDATE | Pending
284 | Inventory | Adjustment Out Approval | DELETE | Pending
285 | Inventory | Adjustment Out Approval | PRINT | Pending
286 | Inventory | Assembly Job Order | VIEW | Pending
287 | Inventory | Assembly Job Order | NEW | Pending
288 | Inventory | Assembly Job Order | UPDATE | Pending
289 | Inventory | Assembly Job Order | DELETE | Pending
290 | Inventory | Assembly Job Order | PRINT | Pending
291 | Inventory | Assembly Realization | VIEW | Pending
292 | Inventory | Assembly Realization | NEW | Pending
293 | Inventory | Assembly Realization | UPDATE | Pending
294 | Inventory | Assembly Realization | DELETE | Pending
295 | Inventory | Assembly Realization | PRINT | Pending
296 | Inventory | Dock Stock | VIEW | Pending
297 | Inventory | Dock Stock | NEW | Pending
298 | Inventory | Dock Stock | UPDATE | Pending
299 | Inventory | Dock Stock | DELETE | Pending
300 | Inventory | Dock Stock | PRINT | Pending
301 | Inventory | Goods Received Note by Purchase Order | VIEW | Pending
302 | Inventory | Goods Received Note by Purchase Order | NEW | Pending
303 | Inventory | Goods Received Note by Purchase Order | UPDATE | Pending
304 | Inventory | Goods Received Note by Purchase Order | DELETE | Pending
305 | Inventory | Goods Received Note by Purchase Order | PRINT | Pending
306 | Inventory | Rack Mutation | VIEW | Pending
307 | Inventory | Rack Mutation | NEW | Pending
308 | Inventory | Rack Mutation | UPDATE | Pending
309 | Inventory | Rack Mutation | DELETE | Pending
310 | Inventory | Rack Mutation | PRINT | Pending
311 | Inventory | Warehouse Transfer In | VIEW | Pending
312 | Inventory | Warehouse Transfer In | NEW | Pending
313 | Inventory | Warehouse Transfer In | UPDATE | Pending
314 | Inventory | Warehouse Transfer In | DELETE | Pending
315 | Inventory | Warehouse Transfer In | PRINT | Pending
316 | Inventory | Warehouse Transfer Out | VIEW | Pending
317 | Inventory | Warehouse Transfer Out | NEW | Pending
318 | Inventory | Warehouse Transfer Out | UPDATE | Pending
319 | Inventory | Warehouse Transfer Out | DELETE | Pending
320 | Inventory | Warehouse Transfer Out | PRINT | Pending
321 | Master | Asset Category | VIEW | Done
322 | Master | Asset Category | NEW | Done
323 | Master | Asset Category | UPDATE | Done
324 | Master | Asset Category | DELETE | Done
325 | Master | Asset Category | PRINT | Done
326 | Master | Asset Registration | VIEW | Done
327 | Master | Asset Registration | NEW | Done
328 | Master | Asset Registration | UPDATE | Done
329 | Master | Asset Registration | DELETE | Done
330 | Master | Asset Registration | PRINT | Pending
331 | Master | Bank | VIEW | Done
332 | Master | Bank | NEW | Done
333 | Master | Bank | UPDATE | Done
334 | Master | Bank | DELETE | Done
335 | Master | Bank | PRINT | Done
336 | Master | Bank Account | VIEW | Pending
337 | Master | Bank Account | NEW | Done
338 | Master | Bank Account | UPDATE | Done
339 | Master | Bank Account | DELETE | Done
340 | Master | Bank Account | PRINT | Pending
341 | Master | Bill of Material | VIEW | Done
342 | Master | Bill of Material | NEW | Done
343 | Master | Bill of Material | UPDATE | Done
344 | Master | Bill of Material | DELETE | Done
345 | Master | Bill of Material | PRINT | Pending
346 | Master | Branch | VIEW | Done
347 | Master | Branch | NEW | Done
348 | Master | Branch | UPDATE | Done
349 | Master | Branch | DELETE | Done
350 | Master | Branch | PRINT | Pending
351 | Master | Cash Account | VIEW | Done
352 | Master | Cash Account | NEW | Done
353 | Master | Cash Account | UPDATE | Done
354 | Master | Cash Account | DELETE | Done
355 | Master | Cash Account | PRINT | Pending
356 | Master | Chart of Account | VIEW | Done
357 | Master | Chart of Account | NEW | Done
358 | Master | Chart of Account | UPDATE | Done
359 | Master | Chart of Account | DELETE | Done
360 | Master | Chart of Account | PRINT | Pending
361 | Master | City | VIEW | Done
362 | Master | City | NEW | Done
363 | Master | City | UPDATE | Done
364 | Master | City | DELETE | Done
365 | Master | City | PRINT | Done
366 | Master | Co - Driver | VIEW | Done
367 | Master | Co - Driver | NEW | Done
368 | Master | Co - Driver | UPDATE | Done
369 | Master | Co - Driver | DELETE | Done
370 | Master | Co - Driver | PRINT | Pending
371 | Master | Country | VIEW | Done
372 | Master | Country | NEW | Done
373 | Master | Country | UPDATE | Done
374 | Master | Country | DELETE | Done
375 | Master | Country | PRINT | Pending
376 | Master | Currency | VIEW | Done
377 | Master | Currency | NEW | Done
378 | Master | Currency | UPDATE | Done
379 | Master | Currency | DELETE | Done
380 | Master | Currency | PRINT | Pending
381 | Master | Current Stock COGSIDR | VIEW | Done
382 | Master | Current Stock COGSIDR | NEW | Pending
383 | Master | Current Stock COGSIDR | UPDATE | Pending
384 | Master | Current Stock COGSIDR | DELETE | Pending
385 | Master | Current Stock COGSIDR | PRINT | Done
386 | Master | Current Stock Quantiy | VIEW | Done
387 | Master | Current Stock Quantiy | NEW | Pending
388 | Master | Current Stock Quantiy | UPDATE | Pending
389 | Master | Current Stock Quantiy | DELETE | Pending
390 | Master | Current Stock Quantiy | PRINT | Done
391 | Master | Customer | VIEW | Done
392 | Master | Customer | NEW | Done
393 | Master | Customer | UPDATE | Done
394 | Master | Customer | DELETE | Done
395 | Master | Customer | PRINT | Pending
396 | Master | Customer Address | VIEW | Done
397 | Master | Customer Address | NEW | Done
398 | Master | Customer Address | UPDATE | Done
399 | Master | Customer Address | DELETE | Done
400 | Master | Customer Address | PRINT | Pending
401 | Master | Customer Category | VIEW | Done
402 | Master | Customer Category | NEW | Done
403 | Master | Customer Category | UPDATE | Done
404 | Master | Customer Category | DELETE | Done
405 | Master | Customer Category | PRINT | Pending
406 | Master | Customer Contact | VIEW | Done
407 | Master | Customer Contact | NEW | Done
408 | Master | Customer Contact | UPDATE | Done
409 | Master | Customer Contact | DELETE | Done
410 | Master | Distribution Channel | VIEW | Done
411 | Master | Distribution Channel | NEW | Done
412 | Master | Distribution Channel | UPDATE | Done
413 | Master | Distribution Channel | DELETE | Done
414 | Master | Distribution Channel | PRINT | Pending
415 | Master | Driver | VIEW | Done
416 | Master | Driver | NEW | Done
417 | Master | Driver | UPDATE | Done
418 | Master | Driver | DELETE | Done
419 | Master | Driver | PRINT | Pending
420 | Master | Education | VIEW | Done
421 | Master | Education | NEW | Done
422 | Master | Education | UPDATE | Done
423 | Master | Education | DELETE | Done
424 | Master | Education | PRINT | Pending
425 | Master | Employee | VIEW | Done
426 | Master | Employee | NEW | Done
427 | Master | Employee | UPDATE | Done
428 | Master | Employee | DELETE | Done
429 | Master | Employee | PRINT | Pending
430 | Master | Exchange Rate | VIEW | Pending
431 | Master | Exchange Rate | NEW | Pending
432 | Master | Exchange Rate | UPDATE | Pending
433 | Master | Exchange Rate | DELETE | Pending
434 | Master | Expedition | VIEW | Done
435 | Master | Expedition | NEW | Done
436 | Master | Expedition | UPDATE | Done
437 | Master | Expedition | DELETE | Done
438 | Master | Expedition | PRINT | Pending
439 | Master | Island | VIEW | Done
440 | Master | Island | NEW | Done
441 | Master | Island | UPDATE | Done
442 | Master | Island | DELETE | Done
443 | Master | Island | PRINT | Pending
444 | Master | Item | VIEW | Done
445 | Master | Item | NEW | Done
446 | Master | Item | UPDATE | Done
447 | Master | Item | DELETE | Done
448 | Master | Item | PRINT | Pending
449 | Master | Item Brand | VIEW | Done
450 | Master | Item Brand | NEW | Done
451 | Master | Item Brand | UPDATE | Done
452 | Master | Item Brand | DELETE | Done
453 | Master | Item Brand | PRINT | Pending
454 | Master | Item Commission Range | VIEW | Done
455 | Master | Item Commission Range | NEW | Pending
456 | Master | Item Commission Range | UPDATE | Pending
457 | Master | Item Commission Range | DELETE | Pending
458 | Master | Item Commission Range | PRINT | Pending
459 | Master | Item Division | VIEW | Done
460 | Master | Item Division | NEW | Done
461 | Master | Item Division | UPDATE | Done
462 | Master | Item Division | DELETE | Done
463 | Master | Item Division | PRINT | Pending
464 | Master | Item Product Category | VIEW | Done
465 | Master | Item Product Category | NEW | Done
466 | Master | Item Product Category | UPDATE | Done
467 | Master | Item Product Category | DELETE | Done
468 | Master | Item Product Category | PRINT | Pending
469 | Master | Item Product Head | VIEW | Done
470 | Master | Item Product Head | NEW | Done
471 | Master | Item Product Head | UPDATE | Done
472 | Master | Item Product Head | DELETE | Done
473 | Master | Item Product Head | PRINT | Pending
474 | Master | Journal | VIEW | Done
475 | Master | Journal | NEW | Pending
476 | Master | Journal | UPDATE | Done
477 | Master | Payment Term | VIEW | Pending
478 | Master | Payment Term | NEW | Pending
479 | Master | Payment Term | UPDATE | Pending
480 | Master | Payment Term | DELETE | Pending
481 | Master | Payment Term | PRINT | Pending
482 | Master | PPh Type | VIEW | Pending
483 | Master | PPh Type | NEW | Pending
484 | Master | PPh Type | UPDATE | Pending
485 | Master | PPh Type | DELETE | Pending
486 | Master | PPh Type | PRINT | Pending
487 | Master | Price List | VIEW | Pending
488 | Master | Price List | NEW | Pending
489 | Master | Price List | UPDATE | Pending
490 | Master | Price List | DELETE | Pending
491 | Master | Price List | PRINT | Pending
492 | Master | Price List Approval | VIEW | Pending
493 | Master | Price List Approval | NEW | Pending
494 | Master | Price List Approval | UPDATE | Pending
495 | Master | Price List Approval | DELETE | Pending
496 | Master | Price List Approval | PRINT | Pending
497 | Master | Price Type | VIEW | Pending
498 | Master | Price Type | NEW | Pending
499 | Master | Price Type | UPDATE | Pending
500 | Master | Price Type | DELETE | Pending
501 | Master | Price Type | PRINT | Pending
502 | Master | Project | VIEW | Pending
503 | Master | Project | NEW | Pending
504 | Master | Project | UPDATE | Pending
505 | Master | Project | DELETE | Pending
506 | Master | Project | PRINT | Pending
507 | Master | Promo ( Customer ) | VIEW | Pending
508 | Master | Promo ( Customer ) | NEW | Pending
509 | Master | Promo ( Customer ) | UPDATE | Pending
510 | Master | Promo ( Customer ) | DELETE | Pending
511 | Master | Promo ( Customer ) | PRINT | Pending
512 | Master | Promo ( Vendor ) | VIEW | Pending
513 | Master | Promo ( Vendor ) | NEW | Pending
514 | Master | Promo ( Vendor ) | UPDATE | Pending
515 | Master | Promo ( Vendor ) | DELETE | Pending
516 | Master | Promo ( Vendor ) | PRINT | Pending
517 | Master | Promo Category ( Customer ) | VIEW | Pending
518 | Master | Promo Category ( Customer ) | NEW | Pending
519 | Master | Promo Category ( Customer ) | UPDATE | Pending
520 | Master | Promo Category ( Customer ) | DELETE | Pending
521 | Master | Promo Category ( Customer ) | PRINT | Pending
522 | Master | Promo Category ( Vendor ) | VIEW | Pending
523 | Master | Promo Category ( Vendor ) | NEW | Pending
524 | Master | Promo Category ( Vendor ) | UPDATE | Pending
525 | Master | Promo Category ( Vendor ) | DELETE | Pending
526 | Master | Promo Category ( Vendor ) | PRINT | Pending
527 | Master | Province | VIEW | Pending
528 | Master | Province | NEW | Pending
529 | Master | Province | UPDATE | Pending
530 | Master | Province | DELETE | Pending
531 | Master | Province | PRINT | Pending
532 | Master | Purchase Destination | VIEW | Pending
533 | Master | Purchase Destination | NEW | Pending
534 | Master | Purchase Destination | UPDATE | Pending
535 | Master | Purchase Destination | DELETE | Pending
536 | Master | Purchase Destination | PRINT | Pending
537 | Master | Rack | VIEW | Pending
538 | Master | Rack | NEW | Pending
539 | Master | Rack | UPDATE | Pending
540 | Master | Rack | DELETE | Pending
541 | Master | Rack | PRINT | Pending
542 | Master | Rack - Item | VIEW | Pending
543 | Master | Rack - Item | NEW | Pending
544 | Master | Rack - Item | UPDATE | Pending
545 | Master | Rack - Item | DELETE | Pending
546 | Master | Rack - Item | PRINT | Pending
547 | Master | Rack Type | VIEW | Pending
548 | Master | Rack Type | NEW | Pending
549 | Master | Rack Type | UPDATE | Pending
550 | Master | Rack Type | DELETE | Pending
551 | Master | Rack Type | PRINT | Pending
552 | Master | Reason | VIEW | Pending
553 | Master | Reason | NEW | Pending
554 | Master | Reason | UPDATE | Pending
555 | Master | Reason | DELETE | Pending
556 | Master | Reason | PRINT | Pending
557 | Master | Religion | VIEW | Pending
558 | Master | Religion | NEW | Pending
559 | Master | Religion | UPDATE | Pending
560 | Master | Religion | DELETE | Pending
561 | Master | Religion | PRINT | Pending
562 | Master | Sales Person | VIEW | Pending
563 | Master | Sales Person | NEW | Pending
564 | Master | Sales Person | UPDATE | Pending
565 | Master | Sales Person | DELETE | Pending
566 | Master | Sales Person | PRINT | Pending
567 | Master | Target Head Product | VIEW | Pending
568 | Master | Target Head Product | NEW | Pending
569 | Master | Target Head Product | UPDATE | Pending
570 | Master | Target Head Product | DELETE | Pending
571 | Master | Target Head Product | PRINT | Pending
572 | Master | Target Head Product Posting | VIEW | Pending
573 | Master | Target Head Product Posting | NEW | Pending
574 | Master | Target Head Product Posting | UPDATE | Pending
575 | Master | Target Head Product Posting | DELETE | Pending
576 | Master | Target Head Product Posting | PRINT | Pending
577 | Master | Unit Of Measure | VIEW | Pending
578 | Master | Unit Of Measure | NEW | Pending
579 | Master | Unit Of Measure | UPDATE | Pending
580 | Master | Unit Of Measure | DELETE | Pending
581 | Master | Unit Of Measure | PRINT | Pending
582 | Master | Vendor | VIEW | Pending
583 | Master | Vendor | NEW | Pending
584 | Master | Vendor | UPDATE | Pending
585 | Master | Vendor | DELETE | Pending
586 | Master | Vendor | PRINT | Pending
587 | Master | Vendor Category | VIEW | Pending
588 | Master | Vendor Category | NEW | Pending
589 | Master | Vendor Category | UPDATE | Pending
590 | Master | Vendor Category | DELETE | Pending
591 | Master | Vendor Category | PRINT | Pending
592 | Master | Vendor Contact | VIEW | Pending
593 | Master | Vendor Contact | NEW | Pending
594 | Master | Vendor Contact | UPDATE | Pending
595 | Master | Vendor Contact | DELETE | Pending
596 | Master | Vendor Contact | PRINT | Pending
597 | Master | Warehouse | VIEW | Pending
598 | Master | Warehouse | NEW | Pending
599 | Master | Warehouse | UPDATE | Pending
600 | Master | Warehouse | DELETE | Pending
601 | Master | Warehouse | PRINT | Pending
602 | Purchasing | Purchase Order | VIEW | Done
603 | Purchasing | Purchase Order | NEW | Done
604 | Purchasing | Purchase Order | UPDATE | Done
605 | Purchasing | Purchase Order | DELETE | Done
606 | Purchasing | Purchase Order | PRINT | Done
607 | Purchasing | Purchase Order Approval | VIEW
608 | Purchasing | Purchase Order Approval | NEW
609 | Purchasing | Purchase Order Approval | UPDATE
610 | Purchasing | Purchase Order Approval | DELETE
611 | Purchasing | Purchase Order Approval | PRINT
612 | Purchasing | Purchase Order Closing | VIEW
613 | Purchasing | Purchase Order Closing | NEW
614 | Purchasing | Purchase Order Closing | UPDATE
615 | Purchasing | Purchase Order Closing | DELETE
616 | Purchasing | Purchase Order Closing | PRINT
617 | Purchasing | Purchase Request | VIEW
618 | Purchasing | Purchase Request | NEW
619 | Purchasing | Purchase Request | UPDATE
620 | Purchasing | Purchase Request | DELETE
621 | Purchasing | Purchase Request | PRINT
622 | Purchasing | Purchase Request Approval | VIEW
623 | Purchasing | Purchase Request Approval | NEW
624 | Purchasing | Purchase Request Approval | UPDATE
625 | Purchasing | Purchase Request Approval | DELETE
626 | Purchasing | Purchase Request Approval | PRINT
627 | Purchasing | Purchase Request Closing | VIEW
628 | Purchasing | Purchase Request Closing | NEW
629 | Purchasing | Purchase Request Closing | UPDATE
630 | Purchasing | Purchase Request Closing | DELETE
631 | Purchasing | Purchase Request Closing | PRINT
632 | Purchasing | Purchase Request Non Imr | VIEW
633 | Purchasing | Purchase Request Non Imr | NEW
634 | Purchasing | Purchase Request Non Imr | UPDATE
635 | Purchasing | Purchase Request Non Imr | DELETE
636 | Purchasing | Purchase Request Non Imr | PRINT
637 | Purchasing | Purchase Request Non Imr Approval | VIEW
638 | Purchasing | Purchase Request Non Imr Approval | NEW
639 | Purchasing | Purchase Request Non Imr Approval | UPDATE
640 | Purchasing | Purchase Request Non Imr Approval | DELETE
641 | Purchasing | Purchase Request Non Imr Approval | PRINT
642 | Purchasing | Purchase Request Non Imr Closing | VIEW
643 | Purchasing | Purchase Request Non Imr Closing | NEW
644 | Purchasing | Purchase Request Non Imr Closing | UPDATE
645 | Purchasing | Purchase Request Non Imr Closing | DELETE
646 | Purchasing | Purchase Request Non Imr Closing | PRINT
647 | Purchasing | Purchase Return | VIEW
648 | Purchasing | Purchase Return | NEW
649 | Purchasing | Purchase Return | UPDATE
650 | Purchasing | Purchase Return | DELETE
651 | Purchasing | Purchase Return | PRINT
652 | Report Finance | AP Aging | VIEW | Pending
653 | Report Finance | AP Aging | NEW | Pending
654 | Report Finance | AP Aging | UPDATE | Pending
655 | Report Finance | AP Aging | DELETE | Pending
656 | Report Finance | AP Aging | PRINT | Pending
657 | Report Finance | AR Aging | VIEW | Pending
658 | Report Finance | AR Aging | NEW | Pending
659 | Report Finance | AR Aging | UPDATE | Pending
660 | Report Finance | AR Aging | DELETE | Pending
661 | Report Finance | AR Aging | PRINT | Pending
662 | Sales | CONTRACT_REVIEW | VIEW | Pending
663 | Sales | BLANKET_ORDER | NEW | Pending
664 | Sales | BLANKET_ORDER_CLOSING | UPDATE | Pending
665 | Sales | CUSTOMER_PURCHASE_ORDER_RELEASE | DELETE | Pending
666 | Sales | CUSTOMER_PURCHASE_ORDER_TO_BLANKET_ORDER | PRINT | Pending
667 | Sales | CUSTOMER_PURCHASE_ORDER_TO_SALES_ORDER | VIEW | Pending
668 | Sales | SALES_ORDER | NEW | Pending
669 | Sales | SALES_ORDER_CLOSING | UPDATE | Pending
670 | Sales | SALES_ORDER_UNPRICE | DELETE | Pending
671 | Sales | LIST_OF_APPLICABLE_DOCUMENT | PRINT | Pending
672 | Sales | LIST_OF_APPLICABLE_DOCUMENT_UPLOAD | VIEW | Pending
673 | Sales | REQUEST_FOR_QUOTATION | NEW | Pending
674 | Sales | REQUEST_FOR_QUOTATION_APPROVAL | UPDATE | Pending
675 | Sales | SALES_QUOTATION | DELETE | Pending
676 | Sales | SALES_QUOTATION_STATUS | PRINT | Pending
677 | Sales | Picking List Sales Order | VIEW | Done
678 | Sales | Picking List Sales Order | NEW | Done
679 | Sales | Picking List Sales Order | DELETE | Done
680 | Sales | Picking List Sales Order | PRINT | Waiting
681 | Sales | Picking List Sales Order Confirmation | VIEW | Pending
682 | Sales | Picking List Sales Order Confirmation | NEW | Pending
683 | Sales | Picking List Sales Order Confirmation | UPDATE | Pending
684 | Sales | Picking List Sales Order Confirmation | DELETE | Pending
685 | Sales | Picking List Sales Order Confirmation | PRINT | Pending
686 | Sales | Return by Customer | VIEW | Pending
687 | Sales | Return by Customer | NEW | Pending
688 | Sales | Return by Customer | UPDATE | Pending
689 | Sales | Return by Customer | DELETE | Pending
690 | Sales | Return by Customer | PRINT | Pending
691 | Sales | Return by Customer - Confirmation | VIEW | Pending
692 | Sales | Return by Customer - Confirmation | NEW | Pending
693 | Sales | Return by Customer - Confirmation | UPDATE | Pending
694 | Sales | Return by Customer - Confirmation | DELETE | Pending
695 | Sales | Return by Customer - Confirmation | PRINT | Pending
696 | Sales | Return by Delivery Note | VIEW | Pending
697 | Sales | Return by Delivery Note | NEW | Pending
698 | Sales | Return by Delivery Note | UPDATE | Pending
699 | Sales | Return by Delivery Note | DELETE | Pending
700 | Sales | Return by Delivery Note | PRINT | Pending
701 | Sales | Return by Picking List | VIEW | Pending
702 | Sales | Return by Picking List | NEW | Pending
703 | Sales | Return by Picking List | UPDATE | Pending
704 | Sales | Return by Picking List | DELETE | Pending
705 | Sales | Return by Picking List | PRINT | Pending
706 | Sales | Sales Contract | VIEW | Pending
707 | Sales | Sales Contract | NEW | Pending
708 | Sales | Sales Contract | UPDATE | Pending
709 | Sales | Sales Contract | DELETE | Pending
710 | Sales | Sales Contract | PRINT | Pending
711 | Sales | Sales Contract Approval | VIEW | Pending
712 | Sales | Sales Contract Approval | NEW | Pending
713 | Sales | Sales Contract Approval | UPDATE | Pending
714 | Sales | Sales Contract Approval | DELETE | Pending
715 | Sales | Sales Contract Approval | PRINT | Pending
716 | Sales | Sales Contract Closing | VIEW | Pending
717 | Sales | Sales Contract Closing | NEW | Pending
718 | Sales | Sales Contract Closing | UPDATE | Pending
719 | Sales | Sales Contract Closing | DELETE | Pending
720 | Sales | Sales Contract Closing | PRINT | Pending
721 | Sales | Sales Order | VIEW | Done
722 | Sales | Sales Order | NEW | Done
723 | Sales | Sales Order | DELETE | Done
724 | Sales | Sales Order | PRINT | Waiting
725 | Sales | Sales Order Approval | VIEW | Done
726 | Sales | Sales Order Approval | UPDATE | Done
727 | Sales | Sales Order Approval | PRINT | Waiting
728 | Sales | Sales Order Closing | VIEW | Done
729 | Sales | Sales Order Closing | UPDATE | Done
730 | Sales | Tax Invoice Assignment | VIEW | Pending
731 | Sales | Tax Invoice Assignment | NEW | Pending
732 | Sales | Tax Invoice Assignment | UPDATE | Pending
733 | Sales | Tax Invoice Assignment | DELETE | Pending
734 | Sales | Tax Invoice Assignment | PRINT | Pending
735 | Sales | Tax Invoice Registration | VIEW | Pending
736 | Sales | Tax Invoice Registration | NEW | Pending
737 | Sales | Tax Invoice Registration | UPDATE | Pending
738 | Sales | Tax Invoice Registration | DELETE | Pending
739 | Sales | Tax Invoice Registration | PRINT | Pending
740 | Security | Change Password | VIEW | Pending
741 | Security | Change Password | NEW | Pending
742 | Security | Change Password | UPDATE | Pending
743 | Security | Change Password | DELETE | Pending
744 | Security | Change Password | PRINT | Pending
745 | Security | Data Protection | VIEW | Pending
746 | Security | Data Protection | NEW | Pending
747 | Security | Data Protection | UPDATE | Pending
748 | Security | Data Protection | DELETE | Pending
749 | Security | Data Protection | PRINT | Pending
750 | Security | Role | VIEW | Pending
751 | Security | Role | NEW | Pending
752 | Security | Role | UPDATE | Pending
753 | Security | Role | DELETE | Pending
754 | Security | Role | PRINT | Pending
755 | Security | Role Authorization | VIEW | Pending
756 | Security | Role Authorization | NEW | Pending
757 | Security | Role Authorization | UPDATE | Pending
758 | Security | Role Authorization | DELETE | Pending
759 | Security | Role Authorization | PRINT | Pending
760 | Security | User | VIEW | Pending
761 | Security | User | NEW | Pending
762 | Security | User | UPDATE | Pending
763 | Security | User | DELETE | Pending
764 | Security | User | PRINT | Pending
765 | System | Transaction Log | VIEW | Pending
766 | System | Transaction Log | NEW | Pending
767 | System | Transaction Log | UPDATE | Pending
768 | System | Transaction Log | DELETE | Pending
769 | System | Transaction Log | PRINT | Pending